## LEO
Nebraska Broadband Equity, Access, & Deployment (NBEAD)
Project Timeline and Milestones: LEO Projects
Application Name
Enter a deadline for each item below, using October 1, 2026 as a project start date.
1. Permitting/Make Ready: Proof that necessary permits have been requested filed with NBO. Fully executed contracts by all required parties must be submitted to NBO to consider this milestone achieved. |  |  | click here to enter date
| a. Categorical Exclusion Review |  | click here to enter date
| b. Endangered Species Act Section 7 |  | click here to enter date
| c. National Historic Preservation Act (NHPA) Section 106 |  | click here to enter date
| d. Federal agency permits |  | click here to enter date
|  | i. Bureau of Land Management (BLM) ROW Authorization | click here to enter date
|  | ii. Forest Service (FS) Special Uses | click here to enter date
|  | iii. Clean Water Act (CWA) Section 404/Rivers and Harbors Act (RHA) Section 10 – General Permit | click here to enter date
| e. Other (specify) |  | click here to enter date
2. Program closeout submission/Service is available: Confirmation of all completed construction and activation based on testing data, as-builts, and NBO field verification. |  |  | click here to enter date
3. Subscription rate reaches 25% of BSLs covered by the project. |  |  | click here to enter date
4. Subscription rate reaches 50% of BSLs covered by the project. |  |  | click here to enter date